## TIME SCHEDULE
PALA'S DOCUMENTARY FILM - TIME PLAN
2022-03-16
Tea - 4.30 AM
2022-03-16 | CREW CALL- 5:00 AM @ Mederapitiya ¦ Pallegama
|  | Sunrise : 6.14 AM | Sun Set : 6.19 AM
| No | Time | Set Name & Description | Special Notes | Shooting Location | Director's Note | DOP'S Note
|  | 5.00 AM - 7.30 AM | Stablish Shots |  | Mederapitiya¦ Pallegama
Drone Shots
Jungle
B Rolls
BREAKFAST - 8.00 AM - 9.00 AM @ HOTEL
|  | 8.30 AM- 10.30 AM | Pala's Walking ¦ Free Shots | 2 Hrs | Around His House ¦ Jugle
|  | 10.30 AM- 12.45 PM | Pala's Interview | 2 Hrs
LUCNH BREAK - 1.00 PM - 1.50 PM
|  | 2.00 PM | SHOOT START AFTER LUCH
|  | 2.00 PM - 6.00 PM | Pala's Interview |  | Around Hotel ¦ MIDERIPITITYA
|  |  | * Interview | Walking Talking Shots & Ext.. | JUNGLE AREA
* Dark Shots ¦ Shadow play
* Climate Changing Shots ¦ Time Laps
* Narrow Road's EXT..
DAY 01 - END OF SHOOT
2022-03-17 | 2022-03-17
Tea - 4.30 AM
CREW CALL- 5:30 AM @ DENIYAYA TOWN
|  | Sunrise : 6.13 AM | Sun Set : 6.18 AM
|  | 5.30 AM | Deniyaya Town Stablish Shots | Sunrise ¦ Mountain Roads Ext.. | Deniyaya Town
Drone Shots
|  | 7.30 AM | Deniyaya Town Location Pack | Travel to Hotel
BREAKFAST - 8.00 AM - 9.00 AM @ HOTEL
|  | 9.30 AM - 12.50 PM | School Shots with Pala |  | Around Hotel ¦ MIDERIPITITYA
|  |  | * Interview - Pala's | walking talking
LUNCH - 1.00 PM @ SCHOOL
|  | 2.00 PM | Travel - Back to Hotel | Travel
|  | 2.00 PM - 4.00 PM | Battery Charge ¦ Footage Backkup | Crew Rest | At Hotel
|  | 6.00 PM | PARTY
DAY 02 - END OF SHOOT
2022-03-18
Tea - 6.00 AM
BREAKFAST - 8.00 AM - 9.00 AM @ HOTEL
2022-03-18 | CREW CALL- 9.10 AM @ PALLEGAMA - CULTURAL CENTRE
|  | Sunrise : 6.13 AM | Sun Set : 6.18 AM
|  | 9.00 AM - 12.45 PM | Cultural Centre Set Deco Shoot | Time Laps ¦ Hyper Laps ¦ B Rolls | Pallegama
LUNCH - 1.00 PM @ CULTURAL CENTRE
|  | 2.00 PM - 4.45 PM | Cultural Centre Set Deco Shoot | Time Laps ¦ Hyper Laps ¦ B Rolls | Pallegama
|  | 5.00 PM | Go Back to Hotel | Refresh
|  | 5.30 PM - 6.30 PM | Around Hotel Area Footages | Time Laps ¦ B Rolls ¦ Nature Shots | Around Hotel ¦ MIDERIPITITYA
|  | 7.30 PM | Go Back to Cultural Centre | Trvelling | Pallegama Cultural Centre
|  | 8.00 PM - 11.00 PM | Cultural Centre Set Deco Shoot | Time Laps ¦ Dolly Zoom ¦ Sky Shots
|  |  |  | Transition Shots - Time Laps ( Sky ) | Pallegama Cultural Centre
DAY 03 - END OF SHOOT
2022-03-19
2022-03-19
Tea - 6.00 AM
BREAKFAST - 7.00 AM Cultural Centre
CREW CALL- 8.00 AM @ PALLEGAMA - CULTURAL CENTRE
|  | Sunrise : 6.12 AM | Sun Set : 6.18 AM
|  | 8.00 AM - 12.30 PM | Deco Finishing Shots |  | Cultural Centre
|  | 12.30 PM | Go back to Hotel | For Lunch ( Traveling ) ¦ Refresh
LUNCH - 1.00 PM @ HOTEL
|  | 4.30 PM - 5.00 PM | Go Back to Set | Traveling
|  | 5.00 PM - | Spiritual Shots | Setup Eqiuepments | Cultural Centre
|  | Till Morning |  | OVER NIGHT | Cultural Centre
PM please support to Crew.
2022-03-20
Tea - 6.00 AM
2022-03-20 | BREAKFAST - 7.00 AM Cultural Centre
CREW CALL- 8.00 AM @ PALLEGAMA - CULTURAL CENTRE
|  | Sunrise : 6.12 AM | Sun Set : 6.18 AM
|  | TIME PLS | "Diya Kepeema" Mangalyaya
BREAKFAST 7.00 AM @ CULTURAL CENTRE
|  | 8.00 AM - 10.30 AM | Cultural Centre Shots |  | Cultural Centre
|  | 11.00 AM | Go Back to Hotel | Trvelling
LUNCH - 12.30 PM @ HOTEL
|  | 1.30 PM - 5.30 PM | Rest Time ¦ Refresh | Eqiepment ¦ Battrey Charge | Around Hotel ¦ MIDERIPITITYA
Footage Backup
|  | 6.00 PM - 10.00 PM | Pala's Interview | Walking Talking | Around Hotel ¦ MIDERIPITITYA
Dark ¦ Shadow Shots
DAY 05 - END OF SHOOT
2022-03-21
Tea - 5.30 AM
2022-03-21 | BREAKFAST - 7.30 AM @ HOTEL
CREW CALL- 5.30 AM @ HOTEL
|  | Sunrise : 6.11 AM | Sun Set : 6.18 AM
|  | 6.00 AM - 7.00 AM | Balance Shots | Jungle Shots ¦ Drone ¦ B Rolls
BREAKFAST 7.30 AM @ HOTEL
|  | 8.30 AM - 1.00 PM | Uncles's Shots in Jungle |  | Around Hotel ¦ MIDERIPITITYA
|  |  | Pala's Interview |  | Jungle
|  | 1.15 PM | Back to Hotel | Travel
LUNCH - 1.30 PM @ HOTEL
|  | 2.30 PM - 3.45 PM | Rest Time | Battery Charge ¦ Footage Backup | Hotel
|  | 4.00 PM - Till End | Balance Shots with Pala
|  |  | Pala's Interview |  | Around Hotel ¦ MIDERIPITITYA
END OF SHOOT
2022-03-22
BREAKFAST - 7.30 AM @ HOTEL
Travel Back to Colombo

## Shot NO
Camera Shot No's
No | Description | Shot No | Audio No
1 | Drone Shots : Around Hotel ¦ River ¦ Mountain Range
Mederipitiya Bridge ¦ Mederipitiya School
2 | Pala walks to his house - Front Shot | 2
3 | Pala walks to his house - Following Shot - Steady Cam | 3
4 | Pala comes out of the house | 5
5 | Pala comes out of the house - Back shot | 6
6 | Pala walk in talking to with his Mother | 7
7 | Profile shot of Pala's | 8
8 | Pala walk in talking to with his Mother - Steady Follow | 9
9 | Pala walk in talking to with his Mother - Steady Follow | 10 | 12
10 | Pala with his mother - Insdie the house | 11 | 13
11 | Pala with his mother - Insdie the house - Steady Follow | 13 | 14
12 | Pala Explain about Land Boarders - Drone |  | 19
Guide Video in Theena's 5D Cam
13 | Pala - Walk in Talkking - The way he went to School - Narrow road | 14 | 21
14 |  | 15 | 22
15 |  | 16 | 25
16 |  | 17
17 |  | 18
18 |  | 20
19 | Pala - Telling Story about: The way he was scared on the road he went | 23 | 31
| to school & Ext.. | 24
20 | Aout his grand mothers Mud house Ext..
| Audio Continuing till 38 |  | 38
Chip - 02 - Day 01
| Pala's Interview - 01st ¦ In Opp: Hotel Paddy Bund about granduncle burying himself. Lazerus | 1 | 39
21 | jjjj | 2 | 40
3
|  | 4 | 41
|  | 5 | 42
| Time Laps - Sony A7 | 1
Camera Shot No's
No | Description | Shot No | Audio No
1 | Drone Shots : Deniyaya Drone Shots ¦ Map
2 | Deniyaya Old Building | 1
3 | Barrier with Deniyaya Road | 2
4 | Dniyaya Town | 3
5 | Sky Shot | 4
6 | Pallegama Road Entry from Deniyaya | 5
7 | Pallegama Road Zoom Out | 6
8 | Pallegama Road Zoom In | 7
9 | Pala - Pallegama School Walk in Talking | 8 | 5
10 | Pala's Interview - In School ¦ Stage | 10 | 6
Chip 02
11 | Pala's Interview - In Classroom | 1 | 7
Camera Shot No's
No | Description | Shot No | Audio No
1 | Interview - Walk in Talking ¦ The place where pala was imprisoned | 1 | 1
| Isuru's Audio Clip |  | 6
2 | The place where the dead body was cremated | 2
3 | Temple - Walk in Talking | 3 | 7
4 | Pala - Walk in Talking - In the Forest ¦ Night Dark shot | 11 | 15
|  | 23 | 25
Day 04 & 05 --- 18 Sanniya
Camera Shot No's
No | Description | Shot No | Audio No
1 | Pala's Father's Voice Cut - Interview | 2 | 4
2 | Pala's Father's Voice Cut - Interview - C/U | 3 | 5
3 |  | 4 | 6
4 |  | 5 | 7
5 |  | 8 | 10
6 |  | 9 | 13
7 | Pala With His Father - In the Jungle | 13
14
** Drone Shot - In Drone Backup - Jundle - Last Day
*** | **** Day 04 & 05 - 18 Sanniya ****
~~~ END ~~~
Production : Pala's Documentary Film Date : 16.03.2022
Director : Theena Day : 01
Production : Pala's Documentary Film Date : 17.03.2022
Director : Theena Day : 02
Production : Pala's Documentary Film Date : 18.03.2022
Director : Theena Day : 03
Production : Pala's Documentary Film Date : 21.03.2022
Director : Theena Day : 06